## Home
STF | 409
Status date: | 2026-07-29 14:23 |  |  |  |  | NEW
| Manpower (days) |  |  |  | Funding (EUR) |  |  |  |  | Partner contribution (EUR) |  |  |  | % execution
| Days total | Days remun | Days volunt | Average rate | Manp | Subcont | Other | Travel | Total | Days volunt | In-kind contrib | Total contrib | Partner / funded contract | Partner contrib achieved | Manp used / funded
Funded | 60 | 30 | 30 | 300 | 18000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 18000 | 100% | 100% | 100%
Engaged | 60 | 30 | 30 | 300 | 18000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 18000 | 100% | 100% | 100%
remain | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
remain | 60 | 30 | 30 |  | 18000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 18000 | 100% | 100% | 100%
Accepted | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
remain | 60 | 30 | 30 |  | 18000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 18000 | 100% | 100% | 100%
Invoiced |  |  |  |  | #REF! | #REF! | #REF! | 0 | #REF!
remain |  |  |  |  | #REF! | #REF! | #REF! | 0 | #REF!

## STF info
STF | 409 | STF | Temp_code | Status | TB/WG | Funding | Budget line | Title | Subject | Full Title | Start date | End date | Notes | Notes 2
Temp_code | VD | 409 | VD | ACTIVE | MTS | ETSI | FWP | Test TTCN-3 tools | Test TTCN-3 tools | Conformance tests for TTCN-3 tools | 2010-10-04 | 2010-12-10 |  | WI's to be approved in September 2010
Status | ACTIVE
TB/WG | MTS
Funding | ETSI
Budget line | FWP
Title | Test TTCN-3 tools
Subject | Test TTCN-3 tools
Full Title | Conformance tests for TTCN-3 tools
Start date | 2010-10-04
End date | 2010-12-10
Notes | 0
Notes 2 | WI's to be approved in September 2010
'Deliverable' | 'Date'

## Persons
STF | Role | Name | Company | e-mail | Phone | Mobile | Name2 | Name3
409 | STF_LEADER | Zeiss, Benjamin | Institut für Informatik | zeiss@cs.uni-goettingen.de | +49 151 20617388 | +49 551 39-172020 | Mr. Benjamin Zeiss | Benjamin Zeiss
409 | ACTIVE | Stanca-Kaposta, Bogdan | Testing Technologies | stanca@testingtech.com |  | +49 (030) 726 1919 0 | Mr. Bogdan Stanca-Kaposta | Bogdan Stanca-Kaposta
409 | ACTIVE | Kovacs, Andras | BroadBit Slovakia | andras.kovacs@broadbit.com |  | +36 30 2189659 | Mr. Andras Kovacs | Andras Kovacs
STF | Role | Name | Company | e-mail | Phone | Mobile | Name2 | Name3
409 | Chairman | Schulz, Stephan | Conformiq Software Ltd. | stephan.schulz@conformiq.com | +358 40 1980444 |  | Mr. Stephan Schulz | Stephan Schulz
409 | Vice Chairman | Hogrefe, Dieter | Institut für Informatik | hogrefe@informatik.uni-goettingen.de | +49 17 13 45 28 87 | +49 551 39172001 | Mr. Dieter Hogrefe | Dieter Hogrefe
409 | Vice Chairman | Maggiore, Giulio | TELECOM ITALIA S.p.A. | giulio.maggiore@TELECOMITALIA.IT | +393357534819 | +39 06 3688 5505 | Ing. Giulio Maggiore | Giulio Maggiore
409 | Technical Officer | Vreck, Laurent | ETSI | Laurent.vreck@etsi.org | +33 672 285 218 | +33 4 92 94 43 73 | Mr. Laurent Vreck | Laurent Vreck
409 | Support Co-ordinator | Schmidt, Helene | ETSI | helene.schmidt@etsi.org | +33 6 67177346 | +33 4 92 94 43 41 | Mrs. Helene Schmidt | Helene Schmidt

## Fund
STF | 'ETSI budget year' | 'Fund source' | 'Contract ref' | 'Title' | 'Days total' | 'Days_funded' | 'Days volunt' | Rate | 'Manpower EUR' | 'Subcontr EUR' | 'Other EUR' | 'Travel EUR' | Fund total EUR | Description | 'Fund notes' | 'Contract notes'
409 | 2010 | ETSI | ETSI-STF2010 | ETSI STF budget 2010 | 30 | 30 | 0 | 600 | 18000 | 0 | 0 | 0 |  | ETSI STF budget 2010 | 2nd allocation Board#78
409 | 2010 | ETSI | ETSI-STF2010 | ETSI STF budget 2010 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 |  | ETSI STF budget 2010 | 2nd allocation Board#78 voluntary
Total |  |  |  |  | 60 | 30 | 30 |  | 18000 | 0 | 0 | 0 | 0 |  |  | 0

## Contr spent
YEAR | (All) | [5 empty] | Days contracted |  |  |  | Amount contr'd
MONTH | (All) | [5 empty] | Total | Volunt | Travel
[7 empty] | 60 | 30 | 0 |  | 18000
[14 empty] | Type | Data | Status
[14 empty] | Manpower | [5 empty] | Total Days planned | Total Days volunt | Total Amount planned
[14 empty] | Days planned |  | Days volunt |  | Amount planned
STF | contr | Company | Contr status | Contr type | From | To | Days contr total | Days contr volunt | Days contr travel | Rate | Amount contract | Expert | EXPERT_ID | Accepted | Pending | Accepted | Pending | Accepted | Pending
409 | 01 | Universität Göttingen | SIGNED_CONTR | STF EXPERT | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 300 | 6000 | Zeiss, Benjamin | 53898 | 20 |  | 10 |  | 6000 |  | 20 | 10 | 6000
| 02 | BroadBit Slovakia | SIGNED_CONTR | STF EXPERT | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 300 | 6000 | Kovacs, Andras | 41450 | 10 | 10 | 5 | 5 | 3000 | 3000 | 20 | 10 | 6000
| 03 | Testing Technologies | SIGNED_CONTR | STF EXPERT | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 300 | 6000 | Stanca-Kaposta, Bogdan | 42921 | 10 | 10 | 5 | 5 | 3000 | 3000 | 20 | 10 | 6000
Grand Total | [13 empty] | 40 | 20 | 20 | 10 | 12000 | 6000 | 60 | 30 | 18000

## Travels
STF | 'Travel status' | Travel Order | Status | Expert | Subject | Place | Country | Travel start | Travel end | Dur | Prov cost | Actual cost | Estimate cost | Budget Year
Total | [10 empty] | 0 | 0 | 0

## Invoices
Values
STF | contr | Company | Status | Type | Amount contr | Amount accepted | Invoiced total | Spent not invoced | SAGE reference | Invoice date | Invoice number | Invoice description | Amount invoice | Manp | Subcont | Other
409 | 01 | Universität Göttingen | SIGNED_CONTR | STF EXPERT | 6000 | 6000 | 0 | 6000 |  |  |  |  | 0 | 0 | 0 | 0
| 02 | BroadBit Slovakia | SIGNED_CONTR | STF EXPERT | 6000 | 3000 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0
| 03 | Testing Technologies | SIGNED_CONTR | STF EXPERT | 6000 | 3000 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0
Grand Total | [12 empty] | 0 | 0 | 0 | 0

## In kind
STF | Amount due | Balance confirmed | Balance forecast
Total | 0 | 0 | 0
STF | Event type | Event | City | Country | From | To | Num part | Days IK total | Rate | Amount confirmed | Amount forecast | Sign rcvd | Sign OK | Notes | Travel Order | Expert
Total | [9 empty] | 0 | 0

## TS details
STF | Activity | Expert | Local expert | Year | Month | Status | Days TS | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
409 | Test TTCN-3 tools | Kovacs, Andras |  | 2010 | 10 | ACCEPTED | 10 |  |  |  | E 1 | E 1 | E 1 | E 1 | E 1 |  |  | E 1 | E 1 | E 1 | E 1 | E 1
409 | Test TTCN-3 tools | Stanca-Kaposta, Bogdan |  | 2010 | 10 | ACCEPTED | 10 |  |  |  | E 1 | E 1 | E 1 | E 1 | E 1 | [16 empty] | E 1 | E 1 | E 1 | E 1 | E 1
409 | Test TTCN-3 tools | Zeiss, Benjamin |  | 2010 | 10 | ACCEPTED | 10 |  |  |  | E 1 | E 1 | E 1 | E 1 | E 1 |  |  | E 1 | E 1 | E 1 | E 1 | E 1
409 | Test TTCN-3 tools | Kovacs, Andras |  | 2010 | 11 | DONE | 10 | [7 empty] | C 1 | C 1 | C 1 | C 1 | C 1 | [9 empty] | C 1 | C 1 | C 1 | C 1 | C 1
409 | Test TTCN-3 tools | Stanca-Kaposta, Bogdan |  | 2010 | 11 | DONE | 9 | [7 empty] | C 1 | C 1 | [12 empty] | H 1 | H 1 | H 1 | H 1 | H 1 |  |  | H 1 | H 1
409 | Test TTCN-3 tools | Zeiss, Benjamin |  | 2010 | 11 | ACCEPTED | 10 | [7 empty] | C 1 | C 1 | C 1 | C 1 | C 1 | [9 empty] | C 1 | C 1 | C 1 | C 1 | C 1
409 | Test TTCN-3 tools | Stanca-Kaposta, Bogdan |  | 2010 | 12 | PLANNED | 1 | H 1
Total | [6 empty] | 60 | [30 empty] | 0

## Milestones
STF | Code | Prov | OK to pay | Type | Destin | Achieved date | Target date | Original date | Descr | Meeting | Meeting start | Meeting end | Location | Notes 1 | Notes 2 | Document address
409 | A | 1 | 0 | Final | ETSI |  | 2011-01-15 | 2011-01-15 | Final Report and revised TS’s endorsed by the MTS Chairman and approved by correspondence by TC MTS, accepted by the ETSI editHelp for publication. | [6 empty] | U:\STF_Documents\STF409_MTS_Test_TTCN-3_tools\Reports\STF409_A_FinRep_template.doc

## Deliv
STF | Work Item | Std number | Working title | Current status | STATUS_CODE1 | STATUS_CODE1b | Status code | STATUS | Original date | Target date | Achieved date
409 | DTS/MTS-00132-1-T3Conf_ICS | TS | TTCN-3 tool conformance ICS | 1 | 0 |  | 0 | Creation of WI by WG/TB | 2010-05-17 | 2010-05-17 | 2010-05-17
[6 empty] | a | 0a | TB adoption of WI | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 1 |  | 1 | Start of work | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 2 |  | 2 | Early draft | 2010-11-30 | 2010-11-30 | (blank)
[5 empty] | 4 |  | 4 | Stable draft | 2010-12-20 | 2010-12-20 | (blank)
[5 empty] | 6 |  | 6 | Final draft for approval | 2011-01-14 | 2011-01-14 | (blank)
[5 empty] | 8 |  | 8 | TB approval | 2011-02-01 | 2011-02-01 | (blank)
[6 empty] | a | 8A | Draft receipt by ETSI Secretariat | 2011-02-15 | 2011-02-15 | (blank)
[5 empty] | 12 |  | 12 | Publication | 2011-03-15 | 2011-03-15 | (blank)
| DTS/MTS-00132-2-T3Conf_TPs | TS | TTCN-3 tool conformance TPs | 1 | 0 |  | 0 | Creation of WI by WG/TB | 2010-05-17 | 2010-05-17 | 2010-05-17
[6 empty] | a | 0a | TB adoption of WI | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 1 |  | 1 | Start of work | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 2 |  | 2 | Early draft | 2010-11-30 | 2010-11-30 | (blank)
[5 empty] | 4 |  | 4 | Stable draft | 2010-12-20 | 2010-12-20 | (blank)
[5 empty] | 6 |  | 6 | Final draft for approval | 2011-01-14 | 2011-01-14 | (blank)
[5 empty] | 8 |  | 8 | TB approval | 2011-02-01 | 2011-02-01 | (blank)
[6 empty] | a | 8A | Draft receipt by ETSI Secretariat | 2011-02-15 | 2011-02-15 | (blank)
[5 empty] | 12 |  | 12 | Publication | 2011-03-15 | 2011-03-15 | (blank)
| DTS/MTS-00132-3-T3Conf_ATS | TS | TTCN-3 tool conformance ATS | 1 | 0 |  | 0 | Creation of WI by WG/TB | 2010-05-17 | 2010-05-17 | 2010-05-17
[6 empty] | a | 0a | TB adoption of WI | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 1 |  | 1 | Start of work | 2010-05-28 | 2010-05-28 | 2010-05-28
[5 empty] | 2 |  | 2 | Early draft | 2010-11-30 | 2010-11-30 | (blank)
[5 empty] | 4 |  | 4 | Stable draft | 2010-12-30 | 2010-12-30 | (blank)
[5 empty] | 6 |  | 6 | Final draft for approval | 2011-01-14 | 2011-01-14 | (blank)
[5 empty] | 8 |  | 8 | TB approval | 2011-02-01 | 2011-02-01 | (blank)
[6 empty] | a | 8A | Draft receipt by ETSI Secretariat | 2011-02-15 | 2011-02-15 | (blank)
[5 empty] | 12 |  | 12 | Publication | 2011-03-15 | 2011-03-15 | (blank)

## DPCache_!Contr_spent
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | YEAR | MONTH | Type | Status
409 | 01 | 53898 | Zeiss, Benjamin | STF EXPERT | SIGNED_CONTR | Universität Göttingen | Universität Göttingen | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 11 | Manpower | Accepted
409 | 01 | 53898 | Zeiss, Benjamin | STF EXPERT | SIGNED_CONTR | Universität Göttingen | Universität Göttingen | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 10 | Manpower | Accepted
409 | 02 | 41450 | Kovacs, Andras | STF EXPERT | SIGNED_CONTR | BroadBit Slovakia | BroadBit Slovakia | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 10 | Manpower | Accepted
409 | 03 | 42921 | Stanca-Kaposta, Bogdan | STF EXPERT | SIGNED_CONTR | Testing Technologies | Testing Technologies | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 10 | Manpower | Accepted
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | Year | Month | Type | Status
409 | 02 | 41450 | Kovacs, Andras | STF EXPERT | SIGNED_CONTR | BroadBit Slovakia | BroadBit Slovakia | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 11 | Manpower | Pending
409 | 03 | 42921 | Stanca-Kaposta, Bogdan | STF EXPERT | SIGNED_CONTR | Testing Technologies | Testing Technologies | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 11 | Manpower | Pending
409 | 03 | 42921 | Stanca-Kaposta, Bogdan | STF EXPERT | SIGNED_CONTR | Testing Technologies | Testing Technologies | 2010-10-04 | 2010-12-31 | 20 | 10 | 0 | 6000 | 300 | 2010 | 12 | Manpower | Pending
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | Year | Month | Spent_Type | Spent_Status
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | Year | Month | Spent_Type | Spent_Status
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | Year | Month | Spent_Type | Spent_Status
PT_CODE | CONTR_CODE | EXPERT_ID | Expert | CONT_TYPE_CODE | CONT_STATUS_CODE | ORGA_SHORT | Company | ACT_START | ACT_END | Days_contr_total | Days_contr_volunt | Days_contr_travel | Amount_contr | Rate | Year | Month | Spent_Type | Spent_Status