|  | STF 475 – Progress Report for ETSI |  |  |  |
| --- | --- | --- | --- | --- |
|  | Presented to ETSI meeting |  | Author: | Nikolay Pakulin |
|  | MTS#62 | Munich | Date: |  |
|  | 14-May-2014 | 15-May-2014 | Version |  |
|  | Doc ref |  | page 1 of 2 |  |

| STF | 475 |  | STF leader | Nikolay Pakulin |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Stephan Schulz |
|  |  |  | STF Assistant | Elodie Rouveroux |

| STF title: | Conformance test suite for using XML schema with TTCN-3 |
| --- | --- |

| Milestone | A |  | Status | Covers the period until (cut-off date) | 15-May-2014 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress Report#1 approved by MTS#62 plenary (14-15 May 2014); including methodology and initial draft ATS with test case on schema import. The draft documents will be uploaded by the STF Leader on the MTS contributions area of the ETSI Portal before 8 May 2014. |  |  |  |  |
| Achieved |  | Indicate whether the objective has been achieved If the objective is not achieved, give a short explanation in the “remarks” |  |  |  |
| Remarks |  |  |  |  |  |

Achieved dates

| Template | Draft report | TB approval | ETSI approval | Sent to EC | EC approval |
| --- | --- | --- | --- | --- | --- |
| 16-Apr-2014 |  |  |  |  |  |

# Executive summary

XML is increasingly being used as a data format in ETSI and other standard bodies. Consequently, the related TTCN-3 test specifications include the use of XML as it is the case, for example, in testing of IMS Supplementary Services. TC MTS has received an urgent request from 3GPP to create tests for certifying TTCN-3 tools used for User Equipment conformance tests that use XML schema. A significant number of TTCN-3 test toolsets are available on the market (at least 7 commercial tools and 2 internal tools of industrial ETSI members). Most of them support the use of XML.

MTS has established a TTCN-3 Conformance Test Suite covering the part 1 of TTCN-3 “Core Language”. The use of XML schema with TTCN-3 has been standardized by TC MTS separately from the Core Language, in part 9 “TTCN-3: Using XML schema with TTCN-3”, and is therefore not covered by the existing TTCN-3 Conformance Test Suite.

TC MTS’s target with this STF request is to cover all XML features used by the 3GPP UE tests and in overall 80% of all sections of the part 9 “TTCN-3: Using XML schema with TTCN-3” with conformance test cases. This would secure that TTCN-3 test suites using XML schema will compile on multiple TTCN-3 tools, and remove possible misunderstandings and ambiguities when implementing the use of XML schema in TTCN-3 test tools.

Furthermore, other ETSI technical bodies and industrial fora are also using XML together with TTCN-3 as the test specification language, for example ETSI INT and the NTAF (Network Test Automation Forum).

The STF team consists of 4 experts. The STF has elaborated two working sessions of 5 and 4 working days plus some work at home. The STF has defined the ATS structure, the testing method and developed 127 test cases so far, covering 42 sections of part 9 (out of 117 sections of Part 9).

# Introduction

The creation of the XML schema TTCN-3 conformance test specification work will comprise the following tasks:

- Cataloguing of requirements.

- Adapting existing framework used by the Core Language TTCN-3 reference test specification

- Develop tools for the validation of XML encoding/decoding

- Develop the implementation conformance statement (ICS).

- Develop the test suite structure and test purposes (TSS & TP).

- Develop the abstract test suite (ATS) and IXIT

The STF consists 4 experts:

- Nikolay Pakulin, ISPRAS

- Bogdan Stanca-Kaposta, Testing Technologies

- Tomaš Urban, Elvior OU

- Bostian Pintar, Sintesio

The STF session plan contains 5 one-week working sessions with all experts present and 1 extra week with 3 experts present, total 96 remun. days and 24 volunt. days. Working sessions were held on

- Feb. 03-07 at ETSI, Sophia Antipolis

- April 23-26 at Elvior, Tallinn.

Future working sessions are preliminary scheduled for

- Sept. 15-20, home session.

- November, to be defined.

# Contractual milestone

The contractual milestone A, related to this Progress Report #1 is achieved by TB MTS approving this progress report.

# Progress of the work

By now the STF has exploited 42 man-days out of 120. Two face-to-face sessions were organized:

- Feb. 03-07 at ETSI, Sophia Antipolis

- April 23-26 at Elvior, Tallinn.

Home work session was held on April 14-17.

The following results were achieved:

- Defined the structure of the test suite. Conventions on naming, formatting, etc. developed.

- Defined testing method.

- Developed reference implementation of the utility that compares XML documents; used that implementation to validate the ATS in TTworkbench and TestCast.

- Created 127 test cases covering 42 sections of TTCN-3 Part 9.

# Assessment of technical risk, difficulties encountered/expected, unresolved issues

We can underline the following risks connected with the test suite development.

- Complexity of XML Schema language and tricky issues around TTCN3-XML conversion lead to a risk of not meeting the objective “to cover overall 80% of all sections of the part 9”. At the moment 43% of the manpower are consumed, and 35% of sections covered. The covered sections are relatively simple, dealing with simple types mostly. The remaining section of complex content might require more effort per test case.

- Validation of the test suite require from TTCN-3 tool vendors to implement matchFile external file that implements an algorithm to compare XML documents. The deliverable contains a reference implementation in Java based on XmlUnit tool.

  - The first risk is that if vendor implements this function by its own, say, in other language, the result of test execution might be hampered by defects in the implementation in the comparison algorithm.

  - The second risk is the complexity of XML comparison utility. Vendor might give up validation if they consider implementation of matchFile external function prohibitively expensive.

# Proposed changes in the STF work plan

No proposed change.

# Resources requirements

No additional resource is required as per se.

# Changes in the STF Team

There was no change in the STF's composition and no change is foreseen or required.

# Meetings/events attended on behalf of the STF

The STF member Bogdan Stanca-Kaposta has participated in MTS#62 on May 15, where has presented the current report.

# Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| 1-2 October 2014 | Berlin | MTS#63 | TC MTS regular meeting | STF 475 milestone B progress report. | Nikolay Pakulin, Bogdan Stanca-Kaposta |
| Beginning of 2015 | TBD | MTS#64 | TC MTS regular meeting | STF 475 milestone C, Final report. |  |

# STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The STF has communicated with STF 160 experts via joint meeting and email correspondence.

# Technical advice required from the reference Technical Body

No technical issue needs escalation to the Steering Group of the STF or the TC MTC.

# Status of the deliverables

The snapshot of the SVN repository containing the ATS and developed tools is available under https://forge.etsi.org/svn/TTCN3_PART9/tags/release-mts-62/ tag.

The zip archive with the sources of the ATS and tools, including the sources of the reference implementation of XML comparing utility, are attached to this report among contribution to MTS#62 meeting at http://portal.etsi.org/Contribution.aspx?MeetingId=15330

# Next report

The next report is scheduled for: Milestone report B, MTS#63 (1-2 October 2014).

# Any other business

None.